## PMP Calculations
Business case calculations
Value | Calculation | Comment
Present Value | FV/ (1+i)n | Present Value is value of monies spent or received in future; FV - future value; i - interest rate; n - number of time periods (years)
Benefit cost ratio | Benefit / Costs | Example 1,6
Other calculations
Value | Calculation | Comment
Effort | Duration * Resource units | Effort (mandays)
Duration | Effort / Resource units | Duration (working days)
Resource units | No of resources * Capacity | 1,5 if 2 people are available at 75% of capacity
Expected duration for triangular distribution / simple average | (O+M+P)/3 | O=optimistic estimate; M=most likely; P=pessimistic
Expected duration for beta distribution / weighted average / PERT | (O+4M+P)/6 | O=optimistic estimate; M=most likely; P=pessimistic
Standard deviation | (P-0)/6 | Standard deviation (sigma if we cosider normal distribution)
Communication channels | n*(n-1)/2 | n = number of people
EMV (Expected monetary value) | Value * probability
Decision tree |  | It is better to calculate value for each branch (benefits - cost) then multiply by probability
Earned value calculations
Value | Calculation | Comment
PV |  | Planned value - Budgeted cost of work scheduled
EV |  | Earned value - Budgeted cost of work performed
AC |  | Actual cost - Actual cost of work performed
BAC |  | Budget at completion - total planned value of the project
SV | EV-PV | Schedule variance (>0 ahead of schedule, <0 behind schedule)
CV | EV-AC | Cost variance (>0 bellow budged, <0 over budget)
SPI | EV/PV | Schedule performance index (>1 ahead of schedule, <1 behind schedule)
CPI | EV/AC | Cost performance index (>1 bellow budged, <1 over budget)
ETC | BAC-EV | Estimate to complete; Variances will not occur in future
| (BAC-EV)/CPI | Estimate to complete; Variances will recur in future
| New estimate | Estimate to complete; Original estimate was invalid or flawed
EAC | AC+ETC | General fomula to calculate EAC
| AC+BAC-EV | Estimate at completion: Variances will not occur in future
| BAC/CPI | Estimate at completion: Variances will recur in future
VAC | BAC-EAC | Variance at completion: %VAC or VAC<0 Project will be over budget
TCPI | (BAC-EV)/(Target-AC) | Target could be BAC, new estimate or other target