## Formulář rizik
RISK REGISTER AND RISK MANAGEMENT
Project name
Customer
Project manager
Lasr update
ID | Risk decription | Impact (time, budget, scope) | Monetary impact | Type | Probability 1-5 (5 highest) | Impact 1-5 (5 highest) | PxI | Status | Expected date of occurrence | Owner | Strategy | Risk prevention plan | Risk trigger | Contingency plan (response to risk)
1 | Lack of Java developers in later stages of project | Project delayed | 20000 | People | 1 | 1 | 1 | Active |  | Head of delivery | Accept | Talk to the team manager about capacity on a weekly basis | Project delayed > 1 week due to lack of Java Dev | Hire external contractors
2 |  |  |  |  | 2 | 2 | 4
3 |  |  |  |  | 3 | 3 | 9
4 |  |  |  |  | 4 | 4 | 16
5 |  |  |  |  | 5 | 5 | 25
6 |  |  |  |  | 1 | 5 | 5
7 |  |  |  |  | 1 | 5 | 5
Note on P7: [Komentář ve vlákně] Vaše verze aplikace Excel vám umožňuje číst tento komentář ve vlákně, ale jakékoli jeho úpravy se odeberou, pokud se soubor otevře v novější verzi aplikace Excel. Další informace: https://go.microsoft.com/fwlink/?linkid=870924 Komentář: Smazán sloupec - duplicitní