## Issue log
Issue log
ID | Date raised | Status | Subject | Description | Raised by | Risk (ID) | Impact | Priority | Action needed | Assigned to | Due date
1 | 2020-01-20 | New | Copyright fees | To play reproduced music at the event, it will be necessary to pay OSA royalties, which were not calculated. | Karel |  | Budget (increase) | Nízká | Write a playlist and send it to OSA, ensure payment of the assessed fee. | Renata | 2020-02-01
2
3
4
5
6
Note on G3: Autor: Ad id from your risk registr if needed.